## Dashboard
Winnie I-10 × SH-73 / SH-124 Wye — Truck Yard / IOS Validation Model
Planning workbook: compares direct procurement vs. general-contractor retail delivery, with editable assumptions and validation budget.
Metric | Direct Procurement | GC Retail | Difference | Direct Yield | GC Yield | Flag | Notes
Total Development Cost | 2795450.18 | 4849126.8 | 2053676.62 | 16.12% | Direct cost = Budget_Compare yard + support/reserve land basis | Clears | Costs are formula-driven from Budget_Compare.
Base Annual NOI | 450702 | 450702 |  |  |  |  | Base case: $14/night, 70% occupancy, 30% opex (rate band $12-$15).
Max Cost at 12% NOI Floor | 3755850 | 3755850 |  |  |  |  | NOI / 12% floor.
Direct Gap / Cushion | 960399.82 |  |  |  |  | Cushion | Positive means direct cost stays under 12% floor.
GC Gap / Cushion |  | -1093276.8 |  |  |  | Gap | Positive means GC cost stays under 12% floor.
Model posture
Known screen | Representative example; the developer selects the actual site (broker presents available sites). I-10-edge flood screen returns Zone X; wet shrink-swell clay is the cost driver. | Delivery split | Retail GC pricing is modeled separately from direct procurement / CM-managed buying. | Core cost driver | Yard surface section, grading, drainage, entrance, fence, lighting, and security. | Decision | Validation capital before construction capital: geotech, civil ROM, rate comps, owner path.
Exit economics (base $14/night) | Low bulk | Mid operator-pad | High frontage | Read | Source | Status | Notes
Frontage out-parcel gain (5 ac) | 490500 |  |  | 5-ac frontage sold separately; drainage folded into yard | Land_Value | Planning | Uses current listing comps; not appraisal or closed sale
Combined two-year gross gain (base) | 2502537.82 |  |  | Yard income gain + frontage out-parcel, before carry | Land_Value | Planning | Assumes full parcel acquisition and value credit
Navigation
Inputs | Editable assumptions: parcel, geometry, rate, delivery, contingency.
Quantities | Area, surface volume, tonnage, fencing, stalls, and revenue math.
Budget_Compare | Line-item side-by-side: direct procurement vs. GC retail.
Economics | $12–$15/night rate cases (70% occ); NOI-to-cost test.
Soils_Grading | Plain-English soil interpretation and geotech questions.
Validation_Checklist | Institutional validation workstreams and status fields.
Sources | Source URLs and evidence notes.
Optimization_Levers | Illustrative savings levers to improve margin, reduce exposed capital, and protect the 12% return floor.

## Inputs
Inputs — Winnie I-10 × SH-73 / SH-124 Wye Controlled Yard / IOS Validation
Input | Value | Unit | Source / notes
Candidate parcel ID | Representative example | text | Developer selects the actual site; broker presents available sites (iVerify parcel screen, Winnie wye)
Parcel acres | 19.94 | acres | Representative ~20-ac example (mirrors validation example)
Approx. parcel width | 540 | ft | Representative example
Approx. parcel length | 1722 | ft | Representative example
Phase 1 developed area | 10 | acres | Developer concept sketch
Reserve / future area | 9.94 | acres | Formula: parcel acres less Phase 1
Approx. distance to interchange | 0.8 | miles | Representative example
Mapped floodway | 0 | % | iVerify flood screen — sampled points return Zone X (FEMA minimal risk)
Mapped AE / AH floodplain | 0 | % | iVerify flood screen — outside AE/AH; Zone X at the I-10 edge
Mapped hydric soil | see Soils | — | Leton/Meaton units read wet; confirm wetland delineation (NRCS Web Soil Survey)
Parcel relief | minimal | — | Flat coastal-prairie terrace; clay and water table drive civil, not cut/fill
Target NOI-to-cost floor | 12% | % | Opportunity brief return screen
Base nightly space rate | 14 | $/space/night | Model assumption from opportunity brief
Base occupancy | 70% | % | Model assumption from opportunity brief
Base operating expense ratio | 30% | % of gross | Model assumption from opportunity brief
Illustrative spaces | 180 | spaces | Developer concept / site plan
Land basis | 26900 | $/acre | Winnie node basis ~$26,900/ac (iVerify parcel screen, 2025 CAD); replace with broker comps
Aggregate depth - Lean | 6 | inches | Editable planning assumption
Aggregate depth - Base | 8 | inches | Editable planning assumption
Aggregate depth - Heavy | 10 | inches | Editable planning assumption
Tons per cubic yard | 1.5 | tons/CY | Planning conversion; verify by material supplier
Phase-only fence length | 2693.3333 | LF | Formula from parcel width and Phase 1 area
Full parcel fence length | 4524 | LF | Formula from parcel dimensions
Direct procurement CM fee | 6% | % | Planning assumption
GC overhead/profit markup | 15% | % | Planning assumption
Direct contingency | 15% | % | Planning assumption
GC contingency | 20% | % | Planning assumption
Cap rate | 9% | % | Conservative tertiary cap; the market sets the exit
Disposition cost | 4% | % | Model assumption
Master Plan / Residual Land Inputs
Input | Value | Unit | Source / notes
Frontage fuel/operator pad area | 5 | acres | Conceptual master plan; editable
Controlled yard area | 10 | acres | Phase 1 validation case; editable
Support / drainage / utility reserve | 4.94 | acres | Formula: parcel acres less frontage and yard
Remainder after Phase 1 yard | 9.94 | acres | Formula: parcel acres less controlled yard area
Residual land value sheet | Land_Value | sheet | Comps and value scenarios from the Winnie/Chambers County parcel screen (2025 CAD values)

## Quantities
Quantities — Geometry, Surface, Revenue
Metric | Lean | Base | Heavy | Notes
Phase 1 area (acres) | 10 | 10 | 10 | Developed yard area
Phase 1 area (sf) | 435600 | 435600 | 435600 | Acres × 43,560
Surface depth (in) | 6 | 8 | 10 | Editable
Surface volume (CY) | 8066.6667 | 10755.5556 | 13444.4444 | Area × depth / 27
Surface tonnage | 12100 | 16133.3333 | 20166.6667 | CY × tons/CY
Phase-only fence (LF) | 2693.3333 | 2693.3333 | 2693.3333 | For Phase 1 fence budget
Full parcel fence (LF) | 4524 | 4524 | 4524 | For heavy/full perimeter case
Illustrative spaces | 180 | 180 | 180 | Space count
Spaces per acre | 18 | 18 | 18 | Sanity check
Base gross revenue | 643860 | 643860 | 643860 | Spaces × nightly rate × 365 × occupancy

## Budget_Compare
Budget Compare — Direct Procurement vs. GC Retail
Hardcoded unit prices are planning assumptions. Replace blue unit-price cells with local supplier, subcontractor, civil, and CM/GC quotes.
Section | Line item | Basis | Unit | Qty | Direct Unit $ | Direct Cost | GC Unit $ | GC Cost | Notes / source
Land / Site Control | Phase 1 allocated land | Phase 1 acres × land basis | acre | 10 | 30000 | 300000 | 30000 | 300000 | Uses Phase 1 land allocation; full parcel acquisition shown separately.
Land / Site Control | Due diligence / option / legal | LS | LS | 1 | 30000 | 30000 | 45000 | 45000 | Option, title, legal, broker review allowance.
Land / Site Control | Full parcel reserve land (memo) | Reserve acres × land basis | acre | 9.94 | 0 | 0 | 0 | 0 | Memo line: if buying all 19.94 acres, add reserve land separately.
Due Diligence | Survey / topo | LS | LS | 1 | 18000 | 18000 | 25000 | 25000 | Need Texas (SE coastal) survey/topo quote.
Due Diligence | Geotech / test pits | LS | LS | 1 | 18000 | 18000 | 25000 | 25000 | Compaction, PI, R-value/CBR, salts/sulfates if needed.
Due Diligence | Civil concept / drainage / permit support | LS | LS | 1 | 35000 | 35000 | 50000 | 50000 | Civil ROM and preliminary design package.
Due Diligence | SWPPP / permit allowance | LS | LS | 1 | 15000 | 15000 | 25000 | 25000 | TCEQ Construction General Permit / Chambers County process allowance.
Sitework | Clearing / grubbing | Phase 1 acres | acre | 10 | 2000 | 20000 | 3500 | 35000 | Coastal-prairie clearing / site prep assumption.
Sitework | Rough grading / balance site | Phase 1 acres | acre | 10 | 20000 | 200000 | 35000 | 350000 | Assumes cut/fill can largely balance on site.
Sitework | Fine grading / compaction | Phase 1 acres | acre | 10 | 7000 | 70000 | 11000 | 110000 | Finish pad, compact subgrade.
Sitework | Soil stabilization allowance | Phase 1 acres | acre | 10 | 6000 | 60000 | 12000 | 120000 | Cement/lime/geogrid only if geotech indicates.
Surface | Aggregate base / gravel material | Base scenario tonnage | ton | 16133.3333 | 26 | 419466.6667 | 42 | 677600 | Delivered material assumption; replace with supplier quote.
Surface | Place / spread / compact base | Base scenario tonnage | ton | 16133.3333 | 7 | 112933.3333 | 12 | 193600 | Equipment + labor placement.
Surface | Geotextile / geogrid allowance | Phase 1 sf | sf | 435600 | 0.25 | 108900 | 0.55 | 239580 | Allowance; use only if subgrade requires.
Surface | Dust control / millings top course | Phase 1 sf | sf | 435600 | 0.2 | 87120 | 0.5 | 217800 | Alternative to full asphalt; validate locally.
Drainage | Detention / drainage area | LS | LS | 1 | 100000 | 100000 | 160000 | 160000 | Basins, swales, culverts, erosion control allowance.
Access | Entrance throat / apron / gate drive | LS | LS | 1 | 75000 | 75000 | 120000 | 120000 | Widened throat / heavy section at entry.
Security | Perimeter fence - Phase 1 | Phase-only LF | LF | 2693.3333 | 30 | 80800 | 48 | 129280 | Wire/chain-link/barbed-wire style TBD.
Security | Card-operated gate | LS | LS | 1 | 55000 | 55000 | 85000 | 85000 | Access control, keypad/card, barrier, integration.
Security | Cameras / network | LS | LS | 1 | 40000 | 40000 | 65000 | 65000 | Cameras, recorder/cloud, poles, network.
Lighting | LED light poles | Poles | each | 14 | 6000 | 84000 | 9500 | 133000 | Fixture, pole, foundation, install allowance.
Power | Generator / backup power | LS | LS | 1 | 40000 | 40000 | 65000 | 65000 | Initial generator allowance; size TBD.
Power | Electrical distribution | LS | LS | 1 | 60000 | 60000 | 95000 | 95000 | Trenching, conduit, panels, lighting circuits.
Amenities | Gatehouse / office kiosk | LS | LS | 1 | 35000 | 35000 | 55000 | 55000 | Small office/gatehouse or containerized unit.
Amenities | Executive bathroom / restroom unit | LS | LS | 1 | 65000 | 65000 | 95000 | 95000 | Containerized restroom / executive bathroom allowance.
Amenities | Water tank / basic plumbing | LS | LS | 1 | 20000 | 20000 | 35000 | 35000 | If no immediate utility connection.
Amenities | Pump-out / sewer service setup | LS | LS | 1 | 10000 | 10000 | 18000 | 18000 | Holding tank / service setup; not monthly operating cost.
Site Finish | Striping / signs / wheel stops | LS | LS | 1 | 25000 | 25000 | 45000 | 45000 | Wayfinding, striping, signage, safety markings.
Subtotal - hard & soft line items | [5 empty] | 2184220 |  | 3513860
Direct CM / procurement manager fee | [5 empty] | 131053.2
GC overhead / profit | [7 empty] | 527079
Contingency | [5 empty] | 347290.98 |  | 808187.8
Total Development Cost | [5 empty] | 2662564.18 |  | 4849126.8

## Economics
Economics — $12–$15 / Night Yard Case (70% occupancy)
Metric | $12/night | $14/night | $15/night | Direct Budget | GC Budget
Spaces | 180 | 180 | 180
Nightly rate | 12 | 14 | 15
Occupancy | 70% | 70% | 70%
Gross revenue | 551880 | 643860 | 689850
Expense ratio | 30% | 30% | 30%
Operating expenses | 165564 | 193158 | 206955
Annual NOI | 386316 | 450702 | 482895
NOI-to-cost floor | 12% | 12% | 12%
Max cost at floor | 3219300 | 3755850 | 4024125
Total development cost |  |  |  | 2795450.18 | 4849126.8
NOI yield on cost |  |  |  | 16.12% | 9.294%
Pass 12% floor? |  |  |  | YES | NO
Net sale value @ 9% cap less 4% | 4120704 | 4807488 | 5150880 | 4807488 | 4807488
Gross gain / (gap) |  |  |  | 2012037.82 | -41638.8
Gross gain % |  |  |  | 71.98% | -0.8587%
Read of model
Direct procurement | Uses direct purchasing, procurement manager/CM fee, and supplier/subcontractor pricing. Can preserve economics if sitework stays controlled.
GC retail | Uses higher unit pricing plus GC markup and contingency. Useful as a stress/reference case, not necessarily the preferred delivery path.
Primary risk | The main budget variable is surface section and grading. Geotech and civil ROM will decide whether stabilization/geogrid/asphalt quantities are needed.
Use flexibility | A truck yard is the first case. Fuel, operator pad, IOS, and hybrid configurations would carry different cost and revenue lines.
Residual / frontage economics — see Land_Value sheet (clean structure: yard incl. support land + 5-ac frontage).
Source
Land_Value
Land_Value
Land_Value
Land_Value
Economics
Land_Value
Land_Value
Winnie parcel screen

## Soils_Grading
Soils / Grading — Preliminary Developer Interpretation
Soil / item | Parcel share / fact | Plain-English read | Budget implication | Validation test | Source URL
Anahuac | buildable unit | Shrink-swell clay; the more buildable unit on the AOI, but still high-plasticity. | Heavier pavement section and added foundation work — not a simple grading fix. | Confirm PI, swell potential, R-value/CBR, lime/cement stabilization need. | NRCS Web Soil Survey — https://websoilsurvey.nrcs.usda.gov/
Leton / Meaton | wet units | Slow-draining clay over a shallow water table; reads wet and trends toward wetland ground. | Drives on-site detention and can constrain usable area; wetland delineation may apply. | Wetland delineation; geotech for water table, swell, and bearing. | NRCS Web Soil Survey — https://websoilsurvey.nrcs.usda.gov/
Likely-wetland ground | present | Wet soil units mapped on parts of the AOI — a real screen item, not a clean pass. | Detention and possible avoidance/permitting; reduces usable yard where present. | Field delineation; USACE / TCEQ as applicable. | iVerify soil screen / NRCS Web Soil Survey
Flood (I-10 edge sample) | Zone X | Every point sampled inside the boundary returns Zone X — FEMA minimal-risk, outside the mandatory-insurance zone. | Low flood-insurance exposure at the edge; keep detention sized for slow-draining clay. | Confirm FEMA panel and drainage report at the selected parcel. | iVerify flood screen
Relief / grading | minimal (flat) | Flat coastal-prairie terrace; cut/fill is not the driver here — water and clay are. | Grading is minor; detention and surface section carry the cost. | Topo at the parcel; confirm drainage outfall. | iVerify topo screen
Gulf Coast clay grading | Developer read | High-plasticity clay over a shallow water table; a classic SE Texas coastal-prairie civil profile. | Budget carries detention, heavier section, stabilization, and foundation allowances. | Test pits/borings and a geotech report before final budget. | Developer assumption

## Validation_Checklist
Validation Checklist — Winnie I-10 × SH-73 Institutional Package
Workstream | Question | Current read | Evidence now | Next artifact | Budget line | Owner | Status
Development thesis | Is the I-10 × SH-73 / SH-124 wye already a truck-service / overnight-stop node? | Strong preliminary read | Bingo Travel Plaza & JP Truck Stop at the wye; Love's ~15 mi west; SH-73 Port Arthur/Beaumont corridor | Microsite front page | Internal | Michael / NSG | In progress
Parcel geometry | Can a 10-acre yard fit on the 19.94-acre parcel? | Yes, conceptually | 540' × 1,722' parcel; 10 acres uses ~807 LF at 540' width | Developer concept sketch | Site plan | NSG / civil | Draft
Soils | Can the Anahuac / Leton / Meaton clays support an economical yard section? | Needs geotech — clay over a shallow water table | NRCS Web Soil Survey; wet clay + shallow water table flagged | Geotech memo | Geotech | Geotech firm | Open
Grading | Can detention and the surface section be sized for slow-draining clay? | Reasonable to test | Flat coastal terrace; clay and water table, not cut/fill | Rough grading model | Civil ROM | Civil/earthwork | Open
Surface section | What base/top course is enough for trucks? | Unknown; budget has lean/base/heavy paths | Base tonnage calculation | Surface-section memo | Aggregate/base | Civil/contractor | Open
Access / entrance | What throat/permit improvements are needed? | Normal permit/layout item | Interchange context + visible road network | Access sketch / jurisdiction confirmation | Entrance/apron | Civil/County | Open
Zoning / permits | Is truck parking / IOS allowed and what review is required? | Needs confirmation | Chambers County / TxDOT site plan + driveway guidance | Planning confirmation email | Civil/permitting | Broker/NSG | Open
Rate / demand | Can $12-$15/night cases be supported by local demand? | Needs calls/comps | Carrier base, TxDOT 2024 SE Texas Truck Parking Action Plan, corridor stops | Rate comp table + call notes | Internal | Broker/NSG | Open
Owner path | Can site be optioned or controlled without heavy capital? | Needs contact | Owners identified in the iVerify parcel screen (2025 CAD) | Owner path memo | Site control | Broker | Open
Delivery | Direct procurement vs. GC retail? | Direct route may preserve economics | Budget_Compare workbook | Supplier quote table | Budget | NSG/CM | Open

## Sources
Sources and Evidence
Source | Use in workbook | URL / location | Status | Notes
iVerify Report (Winnie wye) | Traffic, parcels, flood, soils, topography, carrier base, truck parking, broker tools | https://iverify.nsgia.com/site-report?id=7 | Uploaded / cited in chat | Full report supports the corridor and parcel screen.
Winnie corridor screen (deal page) | 12% NOI-to-cost floor, base economics, validation path | https://winnie.nsgia.com/ | Uploaded / cited in chat | Deal page; base economics and validation posture.
Chambers County / Texas permitting | Permit/site plan and required submittals | https://www.co.chambers.tx.us/ | Official | Commercial site plan, SWPPP, drainage, access/driveway, ROW/encroachment may apply.
TCEQ Construction General Permit (TXR150000) | Stormwater permitting / SWPPP trigger | https://www.tceq.texas.gov/permitting/stormwater/construction | Official | Construction disturbing 1+ acres may require CGP coverage if discharge criteria apply.
TxDOT bid tabulations / SE Texas Truck Parking Action Plan | Public benchmark for unit pricing | https://www.txdot.gov/ | Official | Public unit-price benchmark and truck-parking supply context; not a substitute for local quotes.
NRCS Web Soil Survey (Winnie AOI) | Soil interpretation | https://websoilsurvey.nrcs.usda.gov/ | Official | Wet shrink-swell clay; Anahuac buildable, Leton/Meaton read wet.
FHWA Jason's Law truck-parking survey | Truck-parking supply | https://ops.fhwa.dot.gov/freight/infrastructure/truck_parking/ | Official | Parking-supply context for the SE Texas corridor.
Land Comp / Market Source | Source type | What it supports | URL | Notes
iVerify parcel screen — Chambers & Jefferson counties | Parcel screen | 1,278 parcels across Chambers & Jefferson; 80 tracts at 10+ ac (~2,001 ac) | https://iverify.nsgia.com/site-report?id=7 | Screen evidence; 2025 CAD values, not closed sales.
Brown — 44139 I-10 (2 parcels) | Parcel-screen tract | ~40 ac; 2025 CAD $271,370 + $90,000 — cleanest private assembly | iVerify parcel screen (2025 CAD) | CAD value; not asking or closed sale.
Thurmon — 44235 I-10 (2 parcels) | Parcel-screen tract | ~39 ac; 2025 CAD $419,740 + $93,650 | iVerify parcel screen (2025 CAD) | CAD value; not asking or closed sale.
Beaumont IOS comp (down-corridor) | Priced product reference | Secured industrial-outdoor-storage property listed at an ~8% cap, 25–40 mi east | https://winnie.nsgia.com/ | Down-corridor priced product; basis at the wye is lower.
Residual land value logic | Model note | Remainder value scenario in Land_Value sheet | Internal model | Broker opinion and appraisal still required.

## Optimization_Levers
Optimization Levers — Bring Cost Back Toward Return Screen
Lever | Budget line | Current direct cost | Possible revised cost | Potential savings | Notes
Surface depth reduction if geotech permits | Aggregate + placement | 532400 | 363000 | 169400 | Compares base 8-inch section to leaner 6-inch section with lower unit assumptions.
Use geotextile only where needed | Geotextile / geogrid | 108900 | 38115 | 70785 | Spot treatment instead of full Phase 1 coverage.
Defer millings / top course | Dust control / millings | 87120 | 21780 | 65340 | Start with aggregate/dust control and add top course after operations prove demand.
Lease/portable restroom instead of executive build-out | Executive bathroom + pump setup | 75000 | 25000 | 50000 | Use service contract/portable executive unit while validating demand.
Lease generator / smaller initial power package | Generator + electrical | 100000 | 65000 | 35000 | Scale power to lighting/gate/cameras first.
Gatehouse as kiosk/container deferment | Gatehouse / office kiosk | 35000 | 15000 | 20000 | Use card gate + cameras; add office later.
Land option instead of Phase 1 land purchase | Land allocation | 300000 | 50000 | 250000 | Option/ground lease/takedown could reduce first capital exposure.
Reduce initial contingency after quotes | Contingency | 347290.98 | 243103.686 | 104187.294 | Contingency can tighten after quotes and civil ROM.
Total potential savings |  |  |  | 764712.294 | Illustrative only; not all levers can necessarily be combined.
Current direct TDC | Optimized direct TDC | Base NOI | Optimized yield | Target floor | Pass?
2662564.18 | 1897851.886 | 450702 | 23.75% | 12% | YES

## Land_Value
Land Value / Remainder Optionality — Winnie I-10 × SH-73 / SH-124 Wye
Purpose: estimate the value of the frontage/operator pad and remaining non-yard acreage. CAD values are tax-assessed (ownership/scale evidence), not market price; the node basis and frontage cases are planning inputs to validate with broker comps.
Source / property | Location | Acres | Ask price | $/acre | Use / zoning notes | Interpretation | Source URL
Brown — 44139 I-10 (2 parcels) | Winnie, TX (Chambers Co.) | 40 | 361370 | 9034.25 | Private assembly near the interchange; unincorporated, uses to confirm | Cleanest private assembly (2025 CAD) | iVerify parcel screen — 2025 CAD ($271,370 + $90,000)
Thurmon — 44235 I-10 (2 parcels) | Winnie, TX (Chambers Co.) | 39 | 513390 | 13163.8462 | Private assembly near the interchange; unincorporated, uses to confirm | Private assembly (2025 CAD) | iVerify parcel screen — 2025 CAD ($419,740 + $93,650)
Beaumont IOS (down-corridor) | Beaumont, TX |  |  |  | Secured industrial outdoor storage | Priced product reference, 25–40 mi east (~8% cap) | https://winnie.nsgia.com/
Node basis (planning) | Winnie wye |  |  | 26900 | Bulk land at the node | Planning basis — used as the low-bulk scenario input | iVerify parcel screen / planning
Benchmark Inputs / Scenario Pricing
Scenario | Basis | $/acre | Notes
Low bulk interchange land | Winnie node basis (iVerify parcel screen / planning) | 26900 | Planning basis for bulk land at the node; replace with broker comps.
Mid operator-pad case | Developer judgment between bulk land and utility-ready 4.1 ac comp | 125000 | Planning placeholder; replace with broker opinion.
High utility/frontage case | High frontage/utility planning case (Winnie wye) | 175000 | High frontage/utility case; planning — replace with broker comp.
Master Plan Acreage and Optionality
Area | Acres | Low value | Mid value | High value | Low $/ac | Mid $/ac | High $/ac | Comment
Frontage fuel / operator pad | 5 | 134500 | 625000 | 875000 | 26900 | 125000 | 175000 | Reserved for fuel, diesel, truck service, operator pad, or ground lease.
Controlled truck & trailer yard - Phase 1 | 10 | 269000 | 1250000 | 1750000 | 26900 | 125000 | 175000 | Primary cash-flow validation use.
Support / drainage / utility / overflow reserve | 4.94 | 132886 | 617500 | 864500 | 26900 | 125000 | 175000 | Balance of site after front pad and yard.
Remainder after Phase 1 yard | 9.94 | 267386 | 1242500 | 1739500 | 26900 | 125000 | 175000 | Frontage pad plus support/reserve acreage; potential sale, lease, or option value.
Economic Impact — Clean Structure (drainage folded into yard; only the 5-ac frontage is sold)
Metric | Value |  |  | Notes
Yard TDC incl. support/drainage land | 2795450.18 |  |  | Yard 10 ac + support 4.94 ac land folded in
Yard income value @ 9% cap (base $14/night) | 4807488 |  |  | From Economics base column
Yard gain | 2012037.82 |  |  | Income sale less yard basis
Frontage out-parcel value (5 ac, mid) | 625000 |  |  | 5 ac × mid $/ac
Frontage out-parcel basis (5 ac) | 134500 |  |  | 5 ac × land basis
Frontage gain | 490500 |  |  | Value less basis
Combined two-year gross gain (base) | 2502537.82 |  |  | Yard + frontage, before carry
Pass 12% floor? | YES |  |  | Base-case yard NOI / yard basis vs 12% floor
The 5-acre frontage/operator pad is the separable value item. The support/drainage/utility reserve is folded into the yard basis and remains functional land for detention, overflow, utilities, and IOS support. Treat frontage value as optionality until broker validation, entitlement path, utilities, and operator interest are confirmed.